Implementation of management plan for the Lake Engure Nature Park

Project LIFE00/NAT/LV/7134

PROGRESS REPORT

Covering period 1 September 2002 – 31 August 2003

Date of the report: 15 September 2003.

|  | Report compiled by: Inga Račinska, project manager, Latvian Fund for Nature. Address: Kronvalda blvd. 4, Riga LV-1050, LATVIA Tel: +371 7 034894 Fax: +371 7 830291 E-mail address: inga@lanet.lv |  |
| --- | --- | --- |

Table of Contents

Section 1. INTRODUCTION	3

1.1.	Background to the project	3

1.2.	Overview of main conservation issues being addressed	3

1.3.	Objectives of the project as defined in application	5

Section 2. SUMMARY	6

2.1. Summary of the activities during report period	6

2.2. Summary table of activities	7

2.3. Milestones during report period and checklist of identifiable products	8

2.4. Problems or difficulties expected	9

Section 3. TECHNICAL REPORT (BY ACTIVITY)	10

APPENDIX	26

Appendix 1 – MAPS	27

Appendix 2 – PICTURES	30

Appendix 3 – CONTRACTS	36

Appendix 4 – PUBLICATIONS	37

Appendix 5 – PARK PERIODICAL	38

Appendix 6 – ARTICLES IN MEDIA	39

Appendix 7 – ORCHID LEAFLET AND INVITATION	40

Appendix 8 – VIDEO “REED MANAGEMENT”	41

Appendix 9 – SUMMARY FINANCIAL REPORT	42

Section 1. INTRODUCTION

Background to the project

The Lake Engure is unique European wetland and one of the most important nature protection sites in Latvia. It has been nationally protected since 1957 (bird reserve 1957–1998, nature park since 1998). Lake Engure is also the Ramsar site since 1995 when Latvia joined the Convention, the Important Bird Area and the potential Natura 2000 site. The site holds 15 species and 3 habitats of Community importance listed in Bird and Habitat Directives, as well as 18 species of Bern Convention.

Both, national and international nature conservation authorities have recognized the importance of this site. It resulted in several projects for conservation and management funded by both national and international organisations. The most recent of these projects was the elaboration of Management Plan for Lake Engure Nature Park funded by the Swedish Environmental Protection Agency and Latvian Environmental Protection fund. LIFE project is based on this management plan, it aims at implementation of the most urgent management measures foreseen in the management plan, elaborated by joint efforts of Latvian Fund for Nature, Ministry of Environmental Protection and Regional Development of Latvia and local communities. The objective of the plan is the conservation of 5 fish and 3 plant species listed in the Annex 2 of Directive 92/43/EEC, 3 bird species of Directive 79/409/EEC and 18 habitats listed in the Annex 1 of Habitats Directive. Management actions proposed in the plan will contribute to the economic development of the region bringing more income and creating new jobs in the region with high unemployment level.

Overview of main conservation issues being addressed

Main threats to the biological diversity and the amount of bird populations in the Lake Engure Nature Park are overgrowing of the lake by reed, overgrowing of meadows both at the lake and sea. Lack of public involvement and awareness is obstacle to successful implementation of regulations and the management plan.

Overgrowing of the lake by reed, merging of separate reed-beds is considered very significant threat to the lake Engure. Main causes of the overgrowing are lowering of lake levels in 1842, intensive pollution with nutrients from agricultural runoff in the 1960s - 1980s, accumulation of organic material in lake sediments and termination of reed harvest.  Project is addressing this threat by actions C.2., D.2. and D.3.

Loss of meadow habitats and overgrowing of calcareous fens is another dangerous trend, leading to disappearance of such bird species as Crex crex and all Limicolae species, as well as numerous plant species, such as Liparis loeselii (L.) Rich and others. Several habitats of Community importance are in danger of disappearing due to this threat, such as Boreal Baltic coastal meadows, Molinia meadows on calcareous, peaty or clayey-silt-laden soils, Northern boreal alluvial meadows and Calcareous fens with Cladium mariscus and species of the Caricion davalliana. Project is addressing this threat by actions A.1., A.2., C.1., C.3., C.4., D.1. and D.3.

Uncontrolled, illegal and increasing rate of forest cutting is nationwide threat and the result of such actions is that the mid-aged, old and over-age stands have very few elements favouring biological diversity: (large trees, standing dead trees, broken stems, wind-throws of old age, trees with hollows (>25 cm diameter). Therefore, there are no forests that have developed in the longer term without anthropogenic impact. As a result of sanitary cutting, in most of the territory, stands have low stem density, stumps of variable age, stumps from wind-broken trees, and the vegetation has been disturbed by vehicles.

A negative trend that has been increasing in importance since renewal of independence is uncontrolled harvest by private forest owners. Continuation of this process, together with further drainage of forests would intensify the threat to biological diversity in the Lake Engure Nature park forests, and such important habitats as Transition mires and quaking bogs, Alluvial forests with Alnus glutinosa and Fraxinus excelsior (Alno-Padion, Alnion incanae, Salicon albae, Fennoscandian deciduous swamp woods and Bog woodland.

This threat is addressed by actions A.1., B.1. and D.4.

Many habitats and species are influenced by violation of the nature protection regime in Lake Engure Nature park. By actions D.4. and E.3. , project is addressing following threats:

- Violation of fishing and hunting regulations (violation of allowed net length limits, angling and net fishing out of season or in forbidden locations, use of banned fishing instruments and unregistered fishing craft),

- Violation of hunting regulations (hunting in the restricted nature protection territory, use of electrical engines during hunting, use of banned ammunition types),

- Violation of regulations concerning boating stations  (allowed boat number exceeded, clients are not informed of regulations).

Uncontrolled tourism and visitor activities along the sea is another nationwide threat, endangering many important coastal habitats, such as Embryonic shifting dunes, Shifting dunes along the shoreline with Ammophila arenaria (white dunes), Fixed coastal dunes with herbaceous vegetation (grey dunes), Wooded dunes of the Atlantic, Continental and Boreal region.

The negative effects have been caused by the following factors:

- insufficient number of  recreational sites with public services along the seashore,

- insufficiently developed seashore management (refuse collection, regeneration and tending of recreational sites),

- lack of information and control (insufficient information on the LENP regulations regarding protection and use, and insufficient information on beach  and dune ecology, plants and animals).

Project is addressing the issue by providing more information about the regime and values, establishing infrastructure for nature friendly tourism, as well as by enforcing the control in the LENP (Actions D.4., E.1., E.2., E.3., E.4., E.5., E.6., E.7., E.8. and E.9.).

Objectives of the project as defined in application

Objectives of this project are as follows:

- Protection of rare and endangered habitats and species,

- Restoration and maintenance of 107 ha of meadows,

- 50 ha of especially valuable forest saved from cutting,

- At least 2000 visitors per year visiting the Lake Engure Nature Park thus contributing to the economic development of the region,

- Basis for further education and management of the Lake Engure Nature Park.