Section 2. SUMMARY

2.1. Summary of the activities during report period

Project “Implementation of management plan for Lake Engure Nature park” was launched in October 2001. Most of the activities, foreseen in project proposal have been successfully undertaken to date and described in following sections. Also those of the activities, modified or delayed are described in following sections.

Interim project report describing actions implemented from 1 October 2001 to 31 August 2002 was submitted in September 2002, this progress report is describing actions implemented from 1 September 2002 to 31 August 2003.

Among main management activities implemented in this period, actions as reed cutting, restoration and maintenance of shore meadows and further development of nature tourism infrastructure should be mentioned as most significant. Monitoring the impact of management measures on species and habitats (Action D.3) is providing the first results and the experience of project is proving to be very useful for other projects, planning grazing management of grasslands.

Development of nature friendly tourism in the area has resulted in increase of numbers of visitors to Lake Engure Nature park up to 4 times. There have been app. 5000 persons visiting LENP in 2003. We have designed and set up the nature trail, called “Orchid trail” (Action E.4) that was opened in June and experienced close to 1000 visitors in 2003.  Information signs (Action E.3) have been set up, building of bird watching towers (Action E.2) is finished, and summer lecture house is in progress.

Second project meadow was restored this year, cattle is already grazing on the meadow. The effectiveness of maintenance of meadows by grazing is proving to be very high - it can be explicitly seen on the first meadow, where large stands of reed have been eliminated. Cattle and horse grazing have raised high interest in public and media, especially our idea to bring Latvian native breed “Latvian Blue cow” to the area. This breed was almost extinct in 1990ties, now it is beginning to recover and reaches up to 100 animals in Latvia. More information about this action please see in description of Action C.3.

The project have been presented in several seminars in Latvia, as well as in Workshop on Agriculture, Wetlands and Water resources, held in Valencia during Global Biodiversity Forum in 15-17 November 2002. The publication of this presentation please see in Appendix 4. Project was also presented during seminar “LIFE-Nature: Experiences and future plans of the Baltic and EU Member states”, held in Vilnius 6-7 March 2003. More information about the publicity of project please see in Chapter “Publicity” in description of action F.2.

We are describing the progress of the project activity by activity in following sections, according to project proposal. Any additional information to the description of activities, such as pictures, copies and summaries of contracts, maps, published articles and other publications etc. are attached in Appendixes 1-8. Please see location of actions on Map 2, Appendix 1. Summary financial report is included in Appendix 9.

2.2. Summary table of activities

| Number of action | Action | Time plan | Status in IV 2002 | Status in IV 2003 |
| --- | --- | --- | --- | --- |
| A.1. | Digital mapping of habitats of Community importance in LENP | II-IV 2002 | In progress | In progress |
| A.2. | Agreements and contracts with local farmers about keeping the cattle of LENP | IV 2001 – I 2002 | Delayed until 2003 | Accomplished |
| B.1. | Purchase of forest land from 5 private owners in reserve zone | IV 2001 – I 2002 | Delayed until 2003 | Delayed until December 2003 |
| C.1. | Restoration of shore meadows, calcareous meadows and meadows on islands | I-II 2002 | Accomplished in August 2002. | Accomplished |
| C.2. | Purchase of reed cutting machine | IV 2001 – II 2002 | Accomplished in June 2002 | Accomplished |
| C.3. | Purchase of cattle for grazing management in LENP | I-II 2002 | Accomplished in January-August 2002 | Accomplished, more cattle to be bought in 2004 |
| C.4. | Building of fences for keeping the cattle | II 2002, I 2003, I 2004 | Accomplished in June 2002, next fence planned in I 2003. | Accomplished (2 meadows), next fence planned in I 2004. |
| D.1. | Maintaining shore, island and coastal meadows and calcareous fens by grazing | III 2002 – III 2004 | In progress | In progress |
| D.2. | Reed cutting | III 2002, III 2003, III 2004 | In progress | In progress |
| D.3. | Monitoring the effect of management measures on habitats and species | II 2002 – III 2004 | In progress | In progress |
| D.4. | Ensuring adequate control and protection in LENP | IV 2001 – III 2004 | In progress | In progress |
| E.1. | Building of summer lecture room | I-II 2002 | Delayed. Planned to be delivered in September 2002. | Accomplished |
| E.2. | Construction of 2 bird watching towers | I 2002, I 2003 | 1st tower finished in September 2002 | Accomplished |
| E.3. | Setting up notice boards and border signs at LENP | IV 2001 – I 2002 | In progress. Delayed. | Accomplished |
| E.4. | Construction of nature/tourist path | I-II 2003 | Planned | Accomplished |
| E.5. | Printing 3 booklets about LENP and project | IV 2001, I 2003, II 2004 | 1st booklet printed in IV 2001, next booklets planned to be delivered in time | 1st booklet printed, 2nd booklet delayed until October 2003, 3rd booklet will be delivered in time |
| E.6. | Publication of park periodical | I 2003 – III 2004 | Planned | In progress |
| E.7. | Organising seminars | IV 2001, I 2003, II 2004 | 1st and 2nd seminar organised, 3rd planned to be delivered in time | 1st and 2nd seminar organised, 3rd planned to be delivered in time |
| E.8. | Film about LENP | II-III 2003 | In progress | In progress |
| E.9. | Creating home page of LENP and LIFE project | IV 2001 | Delayed. Home page launched in September 2002 | Accomplished |
| F.1. | Monitoring of project performance | III 2002, III 2003, III 2004 | In progress | In progress |
| F.2. | Administration of the project | IV 2001 – III 2004 | In progress | In progress |
| F.3. | Study Tours | IV 2001, II 2002 | Delayed. 1st Study Tour organised in July 2002 | In progress, planned in March 2004. |
| F.4. | Independent audit of the project | III 2004 | Planned | Planned |

2.3. Milestones during report period and checklist of identifiable products

2.3.1. SUMMARY OF PROJECT MILESTONES

| Milestone | Number of action | Planned | Accomplished |
| --- | --- | --- | --- |
| Valuable forest compartments bought for protection | B.1. | March, 2002 | Planned until December 2003. |
| First meadow habitats restored (The wet shore meadow north of the Ornithological station, including a strip of pine forest) | C.1. | June, 2002 | August, 2002 |
| Reed cutting machine bought | C.2. | June, 2002 | June, 2002 |
| Cattle for grazing bought | C.3. | June, 2002 | January – March 2003 |
| Summer lecture room built | E.1. | June, 2002 | August, 2003 |
| First bird watching tower constructed | E.2. | March, 2002 | September, 2002 |
| Second bird watching tower constructed | E.2. | March, 2003 | July, 2003 |
| Tourist path constructed | E.4. | June, 2003 | June, 2003 |
| Project introduction seminar conducted | E.7. | December, 2001 | January, 2002 |
| 2nd project seminar conducted | E.7. | March, 2003 | August, 2002 |
| Final project seminar conducted | E.7. | September, 2004 | - |
| Film about Lake Engure Nature park and project ready | E.8. | September, 2003 | - |

2.3.2. SUMMARY OF DELIVERABLE PRODUCTS

| Product | Number of action | Planned | Accomplished |
| --- | --- | --- | --- |
| Black and white booklet about LIFE project | E.5. | 31 November, 2001 | 19 November, 2001 |
| Home page of LENP and project | E.9. | 31 December, 2001 | Launched in September, 2002 |
| Digital map with habitats of Community importance in LENP | A.1. | 31 December, 2002 | Planned until December 2003 |
| Full colour booklet about LENP and project | E.5. | 15 February, 2003 | Planned in November 2003 |
| Film about Lake Engure Nature park | E.8. | 30 September, 2003 | Will be ready by the end of project |
| Full colour booklet about results of project | E.5. | 30 September, 2004 | - |

2.4. Problems or difficulties expected

There are no major difficulties recognized at this stage of the project. Some of the actions have been slightly delayed, for different reasons, described below and in Progress sections of respective activities.

Some of the activities have been delayed due to changes in “Individual site protection and use regulation” for Lake Engure Nature Park. This Regulation is defining activities allowed or prohibited in the area, also site zoning and site boundaries. The Regulation will be changed, based on information gathered in our project, providing more detailed description of activities allowed and prohibited. Therefore, we have delayed the issuing of booklet about the site and setting up part of information signs – to include new Rules, determined by Regulation. The Regulation is planned to be adopted by the Cabinet of Ministers before the end of this year.

As for difficulties with land purchase, this has been solved on the project level, but unfortunately no permanent solution to the problem has been found on national level. We are planning to purchase the land in nature park zone of LENP, therefore it probably will be purchased on the name of Lake Engure Nature park fund, but this issue has to be once again clarified with Ministry of Environment. There are another restrictions in national legislation, limiting this activity, but we are working on the solution. Please see more detail on this process in description of action B.2.

Also other delays are being dealt with and will not be the reason for any major changes in the project.

As mentioned in previous report, the support of local population is very important for the project. Project staff has been working on providing the first hand information to local population – via publications in local newspapers (in Engure, Mersrags and Kulciems), also by issuing park periodical (first issue is attached to this report in Appendix 5, second issue is in preparation). Publications include also article in national newspaper “Nature diversity” and national magazine “Environmental News”. Copies of these articles (in Latvian) have been attached in Appendix 6. Regular information about the project is also posted on our website www.ldf.lv.